## Slide 1
BE+ PROJECT
PROJECT CYCLE MANAGEMENT AND ERASMUS+

## Slide 2
BE+ PROJECT
PROJECT CYCLE MANAGEMENT AND ERASMUS+

## Slide 3
WHAT IS A PROJECT?

## Slide 4
WHAT DO WE MEAN BY THAT?
WHAT DISTINGUISHES A PROJECT FROM OTHER HUMAN ACTIVITIES?
WHERE DOES IT ALL START FROM?

## Slide 5
3 KEY ELEMENTS

## Slide 6
TRIPLE CONSTRAINT THEORY
OBJECTIVE
RESOURCES
TIME

## Slide 7
A project is a series of activities aimed at bringing about clearly specified objectives within a defined time-period and with a defined budget.
DEFINITION
European Commission

## Slide 8
EVERY PROJECT IS A PROCESS
What comes first?
What comes after?

## Slide 9
PROJECT CYCLE MANAGEMENT
IS AN ANSWER!
Project Cycle Management (PCM) is a methodology for the management activities and decision-making procedures used during the life-cycle of a project.

## Slide 10
PCM is an approach that helps in doing
the right thing
at the right moment!

## Slide 11
HISTORY OF PCM
Late 1960
Early 1980
Early 1990

## Slide 12
WHICH ARE THE KEY PHASES OF A PROJECT?

## Slide 13
EXCERCISE TIME!

## Slide 14
PLAN YOUR HOLIDAY!

## Slide 15
Your are a group of friends that decides to go on holiday together.
You have to plan your holiday together.
Remember to specify which are the key phases and tell us what
comes first and what comes after.

## Slide 17
P.C.M.
1.
INDICATIVE PROGRAMMING
2.
IDENTIFICATION
3.
FORMULATION
4.
FINANCING
5.
IMPLEMENTATION
6.
EVALUATION

## Slide 18
P.C.M.
2. IDENTIFICATION
This phase focuses on defining the needs and identifying the objectives and results of the project.
3. FORMULATION
  This phase addresses the questions related to the application writing project as well as the planning of the details of the project including roles and resources.
  INDICATIVE PROGRAMMING
This phase is key to start off the process with a clear understing about whoa are the partners and what they have in common
4. FINANCING
This phase is the phase between the submission and the start of the project a activities and includes the assessment from the body as well as the conttay
5. IMPLEMENTATION
This phase concerns the execution of the project and it includes the definition of all project management tools and processes aimed at ensuring the achivement of the project objectives.
This phase focuses on the evaluation of the project and the results achieved This phase can set the ground for further development and follow-up activities
PROJECT CYCLE MANAGEMENT APPROACH
6.
EVALUATION

## Slide 19
P.C.M.
2. IDENTIFICATION
  What need is to be tackled?
  What objective & strategy?
  Who will be the actors?
3. FORMULATION
  How is the project planned?
  What does the application require?
  Are all the information available?
  INDICATIVE PROGRAMMING
  Who are we?
  What interests can we share?
  Who should be involved?
4. FINANCING
  Is the application eligible, valid & bankable?
5. IMPLEMENTATION
  Is the workplan clear & shared?
  Are roles & functions established?
  Are the actors prompted?
6. EVALUATION
  What results have been achieved?
  How are they shared & spread?
  For what further development?
PROJECT CYCLE MANAGEMENT APPROACH

## Slide 20
PART 2

## Slide 21
INDICATIVE PROGRAMMING
Setting the basis for a common work...

## Slide 22
WHO ARE WE
WHAT CAN WE SHARE
What characterizes our local context and why we are interested in the theme
Which aspects of the theme respond to a shared need for exchange and deepening

## Slide 23
WHO ARE WE
Questionnaire
Result of the first focus group
First section of the International strategy of the schools (for those who made it)

## Slide 24
WHAT CAN WE SHARE
Matching the thematic aspect to develop the common thematic framework and central issue
THEMATIC ASPECTS
CENTRAL ISSUE
A
B
Which are most considered ?
How are they interrelated ?
How can they be integrated ?
B
A
How can the previous be summarized
into a wholesome statement ?

## Slide 25
A Common Thematic Framework (CTF) builds on the capacity to interrelate the different needs and experiences tied to the theme
It should be sufficiently inclusive to allow each partner to identify itself with it, and sufficiently exclusive to avoid a too broad and generic focus on the theme
Example

## Slide 26
PART 3

## Slide 27
IDENTIFICATION
Defining the main elements of our common project...

## Slide 28
General knowledge about the funding programme and the type of project
The theme is in line with the priorities and strategy of the schools
The theme is considered relevant by the internal and external stakeholders
Pre-conditions

## Slide 29
THE IDENTIFICATION PHASE
SERVES THE NEED
To focus on the central problem to be tackled
To relate and analyze the different causes of the problem(s)
To design a coherent need-driven strategy

## Slide 30
LOGICAL FRAMEWORK METHODOLOGY
(LFM)

## Slide 31
CONSIDER ALL THE PROBLEMS SPINNING AROUND THE THEME
STEP 1

## Slide 32
Insufficient digital and CLIL skills of teachers
Limited learning experience in STEM subjects
Low Student motivation
Poor critical thinking skills among students
STUDENT PERFORMANCE IN STEM SUBJECTS
Inadequate capacity of students to work in teams
outdated teaching strategies
Lack of knowledge of teaching practices in other countries

## Slide 33
FOCUS THE MOST RELEVANT
PROBLEM TO BE TACKLED
STEP 2

## Slide 34
Insufficient digital and CLIL skills of teachers
Limited learning experience in STEM subjects
Low Student motivation
Poor critical thinking skills among students
STUDENT PERFORMANCE IN STEM SUBJECTS
Inadequate capacity of students to work in teams
outdated teaching strategies
Lack of knowledge of teaching practices in other countries

## Slide 35
ANALYZE CAUSES & EFFECTS
STEP 3

## Slide 36
Limited learning experience in STEM subjects
Central issue/problem
Causes
Effect
Insufficient digital and CLIL skills of teachers
Poor critical thinking skills among students
outdated teaching strategies
Low Student motivation
Inadequate capacity of students to work in teams
POOR STUDENT RESULTS IN STEM SUBJECTS
Lack of knowledge of teaching practices in other countries

## Slide 37
BUILD A TREE OF PROBLEMS REFLECTING YOUR SHARED ANALYSIS OF REALITY
STEP 4

## Slide 38
Limited learning experience in STEM subjects
Poor critical thinking skills among students
Low Student motivation
Insufficient digital and CLIL skills of teachers
Outdated teaching strategies
Inadequate capacity of students to work in teams
POOR STUDENT RESULTS IN STEM SUBJECTS
Lack of knowledge of teaching practices in other countries

## Slide 39
TRANSFORM THE PROBLEM INTO OBJECTIVE AND THE CAUSES INTO RESULTS
STEP 5

## Slide 40
Broader learning experience in STEM subjects
Critical thinking skills among students strengthened
Increased Student motivation
Improved
digital and CLIL skills of teachers
Renewed teaching strategies
Improved capacity of students to work in teams
More knowledge of teaching practices in other countries
IMPROVED STUDENT RESULTS IN STEM SUBJECTS

## Slide 41
LET’S START DEFINING OUR STRATEGY
STEP 6

## Slide 42
SPECIFC OBJECTIVE
EXPECTED RESULTS
oVERALL
OBJECTIVE
IMPROVED STUDENT RESULTS IN STEM SUBJECTS
Broader learning experience in STEM subjects
Critical thinking skills among students strengthened
Increased Student motivation
Improved
digital and CLIL skills of teachers
Renewed teaching strategies
Improved capacity of students to work in teams
More knowledge of teaching practices in other countries

## Slide 43
SPECIFC OBJECTIVE
EXPECTED RESULTS
oVERALL
OBJECTIVE
IMPROVED STUDENT RESULTS IN STEM SUBJECTS
Broader learning experience in STEM subjects
Critical thinking skills among students strengthened
Increased Student motivation
Improved
digital and CLIL skills of teachers
Renewed teaching strategies
Improved capacity of students to work in teams
More knowledge of teaching practices in other countries
WHAT IS TO BE DESIRED AFTER THE PROJECT ?
STRATEGY A
STRATEGY B

## Slide 44
DEFINING OUR STRATEGY
WHICH ACTIVITIES BEST SUIT EACH RESULT
STEP 7

## Slide 45
Broader learning experience in STEM subjects
Critical thinking skills among students strengthened
Increased Student motivation
Renewed teaching strategies
SPECIFC OBJECTIVE
EXPECTED RESULTS
Transnational training meetings
Testing New Methods
Joint work with Swedish, Italian, German and Norwegian students
Visiting workshops and theme parks
Practice Exchange Seminars
Pilot Projects
activities

## Slide 46
STEP 8
SET THE STRATEGY IN THE
LOGICAL FRAMEWORK

## Slide 47
STRATEGY | INDICATORS (objectively identifiable) | SOURCE/MEANS OF VERIFICATION | ASSUMPTIONS AND RISKS
GENERAL OBJECTIVE Student performance in stem subjects improved |  |  | 
SPECIFIC OBJECTIVE SO1: Broader learning experience in STEM subjects |  |  | 
EXPECTED RESULTS R1 Renewed teaching strategies R2 Increased Student motivation R3 Critical thinking skills among students strengthened | IND Increased motivation among 70% of pupils | Questionnaire | 
ACTIVITIES A1.1: Transnational training meetings A1.2: Testing new methods A2.1 Local training Seminars A2.2 Job shadowing A3.1 Transnational seminar A3.2 Pilot projects | IND Number of participants in meetings and seminars IND Number of good practices presented and exchanged to identify new methods IND Number of stakeholders testing new methods | List of participants Forms for collection of files and slides submitted Evaluation questionnaires | Other teachers interested in participating in the experiment